## Sheet1
Test | Expected Outcome | Actual Outcome | What You Did to Fix | Date
Entered various indicators to look for results | No errors, correct winners and losers | shows some teams beating themselves | deleted javaScript and added if statements | 2018-04-05
Showed round 1.50 as team | team name | round 1.50 | removed extra bracket | 2018-04-05
See if Opponent Rating works | lower opponent score wins | higher opponent score won | made opponent ratings negative | 2018-04-06
Read Test File from S3 | [1,2,3,4] | Error - URL Invalid | Put testfile into a folder and copied new path | 2018-04-07
Deploying To Heroku | displays home page | No procfile found | Created procfile and placed in root directory | 2018-04-07
Deploying to Heroku | displayed home page | IO File Not Found error | transferred statics files to AWS | 2018-04-07
Read CSV from S3 bucket | Properly Formatted Data | All the data in one string | Imported Boto3 and read files using that | 2018-04-15
Deploying to Heroku V2 | displayed home page | Import Error Module win32timezone not found | Removed unnecessary imports | 2018-04-15
Generate Bracket for 2015 | Ordered list of winners of each round | Out of Bounds Exceptions for seeds | Imported urllib2 and read seeds with url.open | 2018-04-15
Generate Bracket for 2018 | Ordered list of winners of each round | Out of Bounds Exceptions for seeds | Still Broken, needs fix | 2018-04-15
Display Indicators on Home page | Formatted in a table like structure | All in one big string | added paragraph markers and breaks | 2018-04-16
Properly displayed bracket | Teams Post to correct region of the html | Midwest and West were flipped | Switched the indexes in html for midwest and west regions | 2018-04-16
Linking seeds from AWS Bucket to code | Each team was linked to their proper seed | Out of Bounds Exceptions for Teams | Used Boto3 to read file instead | 2018-04-15
Linking Heroku and S3 Bucket | Heroku server can pull files from database | Failed to Find Database error | Gave secret key and Bucket access name to heroku | 2018-04-14
Accessing Files from S3 Bucket | Can read and write files to the S3 Bucket | Access Denied Error | Made the database open to public | 2018-04-13
Launching website from heroku | Server boots correctly | Host Rejected Error | Added correct url to allowed hosts in settings.py | 2018-04-13
Running app locally | App loads like it would on server | Error - no module named Boto3 | Installed Boto3 to virtualenv | 2018-04-14
Use pandas to read CSV | Correctly reads data | Error - no module named Pandas | Added pandas to requirements.txt | 2018-04-10
Running app on server | App loads and display correctly | Error - no module named urllib | Added urllib to requirements.txt | 2018-04-14
Reading orders.txt from bucket | Reads and stores data to seeds | Stores data correctly, but formatted incorrectly | Called split method on seeds1 to remove whitespace | 2018-04-14