## Sheet1
Test | Expected Outcome | Actual Outcome | What You Did to Fix | Date
Added user input for indicator | Works with indicator, shows percentage and games won | Ran with inputed indicator and showed results | Works with multiple indicators | 2018-03-08
test input kaggle csv files | successfully read in with no problem | seeds and regions were too big (all seasons) | adjust to only seasons after 2013 | 2018-03-13
get names names based on team_id from dataframe | all proper names | only the names in the first region | base on seeds instead of region | 2018-03-13
simulate tourney with tourney order | tourney runs | problem because kaggle data was different format | reformat data based on region/seeds | 2018-03-14
fill actual outcomes arrays | arrays of winning teams | error: data formatted differently than kaggle | adjust outcome csvs based on kaggle format ex: W01 for seed 1 in W region | 2018-03-14
calculate best points with different combos of indicators | different score every time | increasing score | reinitialize best poitns to 0 each time | 2018-03-14
fill results array | predicted array filled properly | same winner every time | fix "winner.append(winner)" 2 vars same name | 2018-03-14
test which indicators are best together | best indicators output | last 2 indicators output | indentation wrong - indent over so its in for loop | 2018-03-14
creating dataframe for team's season statistics from season individual game history
group by win team idea/season aggregate sum | dataframe with sum in each column | columns with data that should not be added i. e. add season year 1000 times | drop those columns from dataframe, set as index to false so we can still access win team ID/season make losing team dataframe | 2018-03-15
make array of team total wins/losses by counting them | list of wins/loss by team ID and season | expected length mismatch | data missing - add missing data manually | 2018-03-15
combine regular season wins and losses and rename columns | dataframe with stat columns per teamID and year | correct | n/a | 2018-03-15
concatinate reg season win and loss stats to one dataframe | regular season dataframe | correct but columns in wrong order | reindex by original dataframe | 2018-03-16
insert team name, win, and loss columns | correct dataframe | added new columns to the end | insert at specific location | 2018-03-16
calculate 3P%, FG%, FT% and games | added 4 cols into dataframe | correct |  | 2018-03-16
made prediction function work w multiple indicators | code works with multiple indicators without passing in weights | invalid type comparrison | pass in list for indicators instead of individually | 2018-03-24
retest prediction function with 2 indicators | code successfully runs like normal with new function | it worked | n/a | 2018-03-24
run kaggle predictor code | give best points | points are too low | add round number + 1 to points because index from 0 | 2018-03-26
run get_points with actual results and actual results | max points 120 | max points 120 | proves best_points works. | 2018-03-26